## AT - Test Suite
Module - RFC - Project Description
TEST SCENARIOS
Test Case # |  | Expected Result | AT Status | Status | TS Status | Tester and Remarks
Account Management and Payments
TS001 | SSO login with Service Enrollment w/o Mobile Number; Meralco Online | SSO Login should be successful. |  |  |  | Melvene
| TC001_Validate SSO login with Service Enrollment w/o Mobile Number; Meralco Online_Facebook | SSO Login should be successful. |  | Deferred
| TC002_Validate SSO login with Service Enrollment w/o Mobile Number; Meralco Online_Google | SSO Login should be successful. |  | Passed
| TC003_Validate SSO login with Service Enrollment w/o Mobile Number; Meralco Online_Apple ID | SSO Login should be successful. |  | Passed
TS002 | SSO login w/o Mobile Number and Service Enrollment; Meralco Online | SSO Login should be successful. |  |  |  | Melvene
| TC004_Validate SSO login w/o Mobile Number and Service Enrollment; Meralco Online_Facebook | SSO Login should be successful. |  | Deferred
| TC005_Validate SSO login w/o Mobile Number and Service Enrollment; Meralco Online_Google | SSO Login should be successful. |  | Passed
| TC006_Validate SSO login w/o Mobile Number and Service Enrollment; Meralco Online_Apple ID | SSO Login should be successful. |  | Passed
| TC033_Validate Welcome Email for Apple SSO Users | Welcome Email should be validated. |  | Passed
TS003 | SSO login with Mobile Number; Meralco Online | SSO Login should be successful. |  |  |  | Melvene
| TC007_Validate SSO login with Mobile Number; Meralco Online_Facebook | SSO Login should be successful. |  | Deferred
| TC008_Validate SSO login with Mobile Number; Meralco Online_Google | SSO Login should be successful. |  | Passed
| TC009_Validate SSO login with Mobile Number; Meralco Online_Apple ID | SSO Login should be successful. |  | Passed
TS004 | SSO login with Service Enrollment with Mobile Number; Meralco Online | SSO Login should be successful. |  |  |  | Melvene
| TC010_Validate SSO login with Service Enrollment with Mobile Number; Meralco Online_Facebook | SSO Login should be successful. |  | Deferred
| TC011_Validate SSO login with Service Enrollment with Mobile Number; Meralco Online_Google | SSO Login should be successful. |  | Passed
| TC012_Validate SSO login with Service Enrollment with Mobile Number; Meralco Online_Apple ID | SSO Login should be successful. |  | Passed
TS005 | SSO login with Service Enrollment w/o Mobile Number; Android | SSO Login should be successful. |  |  |  | Menard
| TC013_Validate SSO login with Service Enrollment w/o Mobile Number; Android_Facebook | SSO Login should be successful. |  | Deferred
| TC014_Validate SSO login with Service Enrollment w/o Mobile Number; Android_Google | SSO Login should be successful. | Automated | Passed
TS006 | SSO login w/o Mobile Number and Service Enrollment; Android | SSO Login should be successful. |  |  |  | Menard
| TC015_Validate SSO login w/o Mobile Number and Service Enrollment; Android_Facebook | SSO Login should be successful. |  | Deferred
| TC016_Validate SSO login w/o Mobile Number and Service Enrollment; Android_Google | SSO Login should be successful. | Automated | Passed |  |  | Manual Click of generation date because it is undetected
TS007 | SSO login with Mobile Number; Android | SSO Login should be successful. |  |  |  | Menard
| TC017_Validate SSO login with Mobile Number; Android_Facebook | SSO Login should be successful. |  | Deferred
| TC018_Validate SSO login with Mobile Number; Android_Google | SSO Login should be successful. | Automated | Passed |  |  | Manual Click of generation date because it is undetected As confirmed by bussiness pop up is same as TS006
TS008 | SSO login with Service Enrollment with Mobile Number; Android | SSO Login should be successful. |  |  |  | Menard
| TC019_Validate SSO login with Service Enrollment with Mobile Number; Android_Facebook | SSO Login should be successful. |  | Deferred
| TC020_Validate SSO login with Service Enrollment with Mobile Number; Android_Google | SSO Login should be successful. | Automated | Passed
TS009 | SSO login with Service Enrollment w/o Mobile Number; iOS | SSO Login should be successful. |  |  |  | Menard
| TC021_Validate SSO login with Service Enrollment w/o Mobile Number; iOS_Facebook | SSO Login should be successful. |  | Deferred
| TC022_Validate SSO login with Service Enrollment w/o Mobile Number; iOS_Google | SSO Login should be successful. |  | Passed
| TC023_Validate SSO login with Service Enrollment w/o Mobile Number; iOS_Apple ID | SSO Login should be successful. |  | Passed
TS010 | SSO login w/o Mobile Number and Service Enrollment; iOS | SSO Login should be successful. |  |  |  | Menard
| TC024_Validate SSO login w/o Mobile Number and Service Enrollment; iOS_Facebook | SSO Login should be successful. |  | Deferred
| TC025_Validate SSO login w/o Mobile Number and Service Enrollment; iOS_Google | SSO Login should be successful. |  | Passed
| TC026_Validate SSO login w/o Mobile Number and Service Enrollment; iOS_Apple ID | SSO Login should be successful. |  | Passed
| TC033_Validate Welcome Email for Apple SSO Users | Welcome Email should be validated. |  | Passed
TS011 | SSO login with Mobile Number; iOS | SSO Login should be successful. |  |  |  | Menard
| TC027_Validate SSO login with Mobile Number; iOS_Facebook | SSO Login should be successful. |  | Deferred
| TC028_Validate SSO login with Mobile Number; iOS_Google | SSO Login should be successful. |  | Passed
| TC029_Validate SSO login with Mobile Number; iOS_Apple ID | SSO Login should be successful. |  | Passed
TS012 | SSO login with Service Enrollment with Mobile Number; iOS | SSO Login should be successful. |  |  |  | Menard
| TC030_Validate SSO login with Service Enrollment with Mobile Number; iOS_Facebook | SSO Login should be successful. |  | Deferred
| TC031_Validate SSO login with Service Enrollment with Mobile Number; iOS_Google | SSO Login should be successful. |  | Passed
| TC032_Validate SSO login with Service Enrollment with Mobile Number; iOS_Apple ID | SSO Login should be successful. |  | Passed
Others - Notification Inbox
TS013 | Validate Notification Inbox; Tap Notification Row_Android | User should be able to validate notification inbox. |  |  |  | Melvene | Notifications are not reusable
Precondition | User should be logged in to Meralco Mobile App |  |  |  |  | reg312022@yopmail.com Password@01
| TC075_Validate Tap Notification Row in Notification Inbox_Android | Notification should turn into grey indicating it is read. | Automated | Passed |  | 1 Retest - CTS-204
| TC038_Validate Notification Bell in Overview Page | * If there is unread notification, red dot should appear beside the Notification Bell. * If all notifications are in read state, red dot should not appear beside the Notification Bell. * If notification is empty, red dot should not appear beside the Notification Bell. | Automated | Passed |  | 1 Retest - CTS-204
TS014 | Validate Notification Inbox; Tap Notification Row_iOS | User should be able to validate notification inbox. |  |  |  | Menard
Precondition | User should be logged in to Meralco Mobile App
| TC076_Validate Tap Notification Row in Notification Inbox_iOS | Notification should turn into grey indicating it is read. |  | Passed
| TC038_Validate Notification Bell in Overview Page | * If there is unread notification, red dot should appear beside the Notification Bell. * If all notifications are in read state, red dot should not appear beside the Notification Bell. * If notification is empty, red dot should not appear beside the Notification Bell. |  | Passed |  | forpayments@yopmail.com P@$$word123456
TS015 | Validate Notification Inbox; Clear All Button_Android | User should be able to validate notification inbox. |  |  |  | Melvene | Notifications are not reusable
Precondition | User should be logged in to Meralco Mobile App |  |  |  |  | reg312022@yopmail.com Password@01
| TC034_Validate Clear All Button in Notification Inbox_Android | All notifications should be deleted; A popup message should appear; Customer should be redirected to Overview Page.; Red dot beside the Notification Bell should be removed. | Automated | Passed |  | 1 Retest - CTS-204
TS016 | Validate Notification Inbox; Clear All Button_iOS | User should be able to validate notification inbox. |  |  |  | Menard
Precondition | User should be logged in to Meralco Mobile App
| TC035_Validate Clear All Button in Notification Inbox_iOS | All notifications should be deleted; A popup message should appear; Customer should be redirected to Overview Page.; Red dot beside the Notification Bell should be removed. |  | Passed |  | forpayments@yopmail.com P@$$word123456
TS017 | Validate Notification Inbox; Trash Icon Button_Android | User should be able to validate notification inbox. |  |  |  | Melvene | Notifications are not reusable
Precondition | User should be logged in to Meralco Mobile App |  |  |  |  | reg312022@yopmail.com Password@01
| TC036_Validate Trash Icon button in Notification Inbox_Android | Notification should be deleted | Automated | Passed |  | 1 Retest - CTS-204
| TC038_Validate Notification Bell in Overview Page | * If there is unread notification, red dot should appear beside the Notification Bell. * If all notifications are in read state, red dot should not appear beside the Notification Bell. * If notification is empty, red dot should not appear beside the Notification Bell. | Automated | Passed |  | 1 Retest - CTS-204
TS018 | Validate Notification Inbox; Trash Icon Button_iOS | User should be able to validate notification inbox. |  |  |  | Menard
Precondition | User should be logged in to Meralco Mobile App
| TC037_Validate Trash Icon button in Notification Inbox_iOS | Notification should be deleted |  | Passed
| TC038_Validate Notification Bell in Overview Page | * If there is unread notification, red dot should appear beside the Notification Bell. * If all notifications are in read state, red dot should not appear beside the Notification Bell. * If notification is empty, red dot should not appear beside the Notification Bell. |  | Passed |  | forpayments@yopmail.com P@$$word123456
Account Management - BIZ Service Prompt
TS019 | Validate Prompt After Successful Enrollment of BIZ Service in MO Account_Meralco Online | Prompt should be validated. |  |  |  | Menard
| TC039_Enroll BIZ Service in MO Account_Meralco Online | BIZ Service Enrollment should be successful; Prompt should be validated. |  | Passed
TS020 | Validate Prompt After Successful Enrollment of BIZ Service in MO Account_Android | Prompt should be validated. |  |  |  | Menard
| TC040_Enroll BIZ Service in MO Account_Android | BIZ Service Enrollment should be successful; Prompt should be validated. |  | Passed
TS021 | Validate Prompt After Successful Enrollment of BIZ Service in MO Account_iOS | Prompt should be validated. |  |  |  | Menard
| TC041_Enroll BIZ Service in MO Account_iOS | BIZ Service Enrollment should be successful; Prompt should be validated. |  | Passed
Account Management - Profile Information; Landline Field
TS022 | Validate Adding Area Code in Landline Field; Profile Information_Meralco Online | Landline field should be validated. |  |  |  | Melvene
Precondition | User should be logged in to Meralco Online
| TC042_Add Area Code in Landline Field_Meralco Online | User should be able to include area code in landline field. |  | Passed
TS023 | Validate Adding Area Code in Landline Field; Profile Information_Android | Landline field should be validated. |  |  |  | Menard
Precondition | User should be logged in to Meralco Online
| TC043_Add Area Code in Landline Field_Android | User should be able to include area code in landline field. | Automated | Passed
TS024 | Validate Adding Area Code in Landline Field; Profile Information_iOS | Landline field should be validated. |  |  |  | Menard
Precondition | User should be logged in to Meralco Online
| TC044_Add Area Code in Landline Field_iOS | User should be able to include area code in landline field. |  | Passed
TS025 | Validate Landline Field; Profile Information; Negative_Meralco Online | Landline field should be validated. |  |  |  | Melvene
Precondition | User should be logged in to Meralco Online
| TC045_Exclude Area Code in Landline Field_Meralco Online | User should be not able to save changes. |  | Passed
TS026 | Validate Landline Field; Profile Information; Negative_Android | Landline field should be validated. |  |  |  | Menard
Precondition | User should be logged in to Meralco Online |  | Automated
| TC046_Exclude Area Code in Landline Field_Android | User should be not able to save changes. |  | Passed
TS027 | Validate Landline Field; Profile Information; Negative_iOS | Landline field should be validated. |  |  |  | Menard
Precondition | User should be logged in to Meralco Online
| TC047_Exclude Area Code in Landline Field_iOS | User should be not able to save changes. |  | Passed
Outage
TS028 | Create Outage Report; No Power - My house/building only_Meralco Online | Outage report should be created. |  |  |  | Arron
| TC048_Create an Outage Report | Outage report should be created. Reference number should be generated. |  | Passed
TS029 | Create Outage Report; No Power - Whole street/block_Meralco Online | Outage report should be created. |  |  |  | Arron
| TC048_Create an Outage Report | Outage report should be created. Reference number should be generated. |  | Passed
TS030 | Create Outage Report; Unstable Power_Meralco Online | Outage report should be created. |  |  |  | Arron
| TC048_Create an Outage Report | Outage report should be created. Reference number should be generated. |  | Passed
TS031 | Create Outage Report; Streetlight Concern_Meralco Online | Outage report should be created. |  |  |  | Arron
| TC048_Create an Outage Report | Outage report should be created. Reference number should be generated. |  | Passed
TS032 | Create Outage Report; Safety Concern_Meralco Online | Outage report should be created. |  |  |  | Arron
| TC048_Create an Outage Report | Outage report should be created. Reference number should be generated. |  | Passed
Bills and Payments
TS033 | Validate APA Unenrollment Button in Accounts Management_Meralco Online | APA Unenrollment Button should be validated. |  |  |  | Melvene
Precondition | SIN should be already enrolled to APA.
| TC049_Validate APA Unenrollment Button | User should be redirected to APA Unenrollment Form. |  | Passed
Service Application - Captcha; Guest User
TS034 | New Service Application in CXE Apply; Individual_Validation of Captcha | Captcha should be validated. |  |  |  | Arron
| TC050_Create New Service Application_Individual | Service Request should be successful; Captcha should be validated. |  | Passed
| TC061_Validate Case Number in CXE | Case Number should be validated in CXE. |  | Passed
TS035 | New Service Application in CXE Apply; Business_Validation of Captcha | Captcha should be validated. |  |  | Automated | Arron
| TC051_Create New Service Application_Business | Service Request should be successful; Captcha should be validated. |  | Passed
| TC061_Validate Case Number in CXE | Case Number should be validated in CXE. |  | Passed
TS036 | New Service Application in CXE Apply; Contractor_Validation of Captcha | Captcha should be validated. |  |  | Automated | Arron | Need to produce screenshot
| TC052_Create New Service Application_Contractor | Service Request should be successful; Captcha should be validated. |  | Passed
| TC061_Validate Case Number in CXE | Case Number should be validated in CXE. |  | Passed
TS037 | Modification of Electric Service in CXE Apply; Individual_Validation of Captcha | Captcha should be validated. |  |  |  | Arron
Precondition | Service should be active.
| TC053_Modification of Electric Service_Individual | Service Request should be successful; Captcha should be validated. |  | Passed
| TC061_Validate Case Number in CXE | Case Number should be validated in CXE. |  | Passed
TS038 | Modification of Electric Service in CXE Apply; Business_Validation of Captcha | Captcha should be validated. |  |  |  | Arron
Precondition | Service should be active.
| TC054_Modification of Electric Service_Business | Service Request should be successful; Captcha should be validated. |  | Passed
| TC061_Validate Case Number in CXE | Case Number should be validated in CXE. |  | Passed
TS039 | Modification of Electric Service in CXE Apply; Contractor_Validation of Captcha | Captcha should be validated. |  |  |  | Arron
Precondition | Service should be active.
| TC055_Modification of Electric Service_Contractor | Service Request should be successful; Captcha should be validated. |  | Passed
| TC061_Validate Case Number in CXE | Case Number should be validated in CXE. |  | Passed
TS040 | Termination of Electric Service in CXE Apply; Individual_Validation of Captcha | Captcha should be validated. |  |  |  | Arron
Precondition | Service should be active.
| TC056_Termination of Electric Service_Individual | Service Request should be successful; Captcha should be validated. |  | Passed
| TC061_Validate Case Number in CXE | Case Number should be validated in CXE. |  | Passed
TS041 | Termination of Electric Service in CXE Apply; Business_Validation of Captcha | Captcha should be validated. |  |  |  | Arron
Precondition | Service should be active.
| TC057_Termination of Electric Service_Business | Service Request should be successful; Captcha should be validated. |  | Passed
| TC061_Validate Case Number in CXE | Case Number should be validated in CXE. |  | Passed
TS042 | Termination of Electric Service in CXE Apply; Contractor_Validation of Captcha | Captcha should be validated. |  |  |  | Arron
Precondition | Service should be active.
| TC058_Termination of Electric Service_Contractor | Service Request should be successful; Captcha should be validated. |  | Passed
| TC061_Validate Case Number in CXE | Case Number should be validated in CXE. |  | Passed
TS043 | Recontract of Electric Service in CXE Apply; Business_Validation of Captcha | Captcha should be validated. |  |  |  | Arron
Precondition | Service should be Terminated.
| TC059_Recontract of Electric Service_Business | Service Request should be successful; Captcha should be validated. |  | Passed
| TC061_Validate Case Number in CXE | Case Number should be validated in CXE. |  | Passed
TS044 | Recontract of Electric Service in CXE Apply; Contractor_Validation of Captcha | Captcha should be validated. |  |  |  | Arron
Precondition | Service should be Terminated.
| TC060_Recontract of Electric Service_Contractor | Service Request should be successful; Captcha should be validated. |  | Passed
| TC061_Validate Case Number in CXE | Case Number should be validated in CXE. |  | Passed
Service Application - Implementing CBM Updates; Web; Link Out to PECCBM Platform
TS045 | Validate Link Out to PECCBM Flatform from MO; Individual | Link out to PECCBM Flatform from MO should be validated. |  |  |  | Menard
TS045 | TC062_Validate Popup Window for PECCBM in Start Service via CXE-Apply; Yes_Individual | User should be redirected to the PECCBM Platform Customer Landing Page. |  | Passed
TS045 | TC063_Validate Popup Window for PECCBM in Start Service via CXE-Apply; No_Individual | User should be redirected to the MO Create Account Page |  | Passed
TS046 | Validate Link Out to PECCBM Flatform from MO; Business | Link out to PECCBM Flatform from MO should be validated. |  |  |  | Menard
TS046 | TC064_Validate Popup Window for PECCBM in Start Service via CXE-Apply; Yes_Business | User should be redirected to the PECCBM Platform Customer Landing Page. |  | Passed
TS046 | TC065_Validate Popup Window for PECCBM in Start Service via CXE-Apply; No_Business | Business Customer should be redirected to the Start a Service Page - Contact Information in MO |  | Passed
TS047 | Validate Link Out to PECCBM Flatform from MO; Contractor | Link out to PECCBM Flatform from MO should be validated. |  |  |  | Menard
TS047 | TC066_Validate Popup Window for PECCBM in Start Service via CXE-Apply; PECCBM_Contractor | PECCBM Contractor should be linked out to the PECCBM Contractor Login Page. |  | Passed
TS047 | TC067_Validate Popup Window for PECCBM in Start Service via CXE-Apply; Contractor_Contractor | Contractor User should be redirected to the Start a Service Page - Contact Information in MO |  | Passed
Service Application - Implementing CBM Updates; Web; Deletion of AMC Availment
TS048 | Validate Deleted AMC Availment in Start Service Page; Value Added Service Tab; Individual | AMC Availment should be deleted in Value Added Service Tab. |  |  |  | Menard
TS048 | TC068_Validate AMC Availment in Value Added Services Tab; Individual | AMC Availment should be validated in Value Added Service Tab. |  | Passed
TS049 | Validate Deleted AMC Availment in Start Service Page; Value Added Service Tab; Business | AMC Availment should be deleted in Value Added Service Tab. |  |  |  | Menard
TS049 | TC069_Validate AMC Availment in Value Added Services Tab; Business | AMC Availment should be validated in Value Added Service Tab. |  | Passed
Service Application - Implementing CBM Updates; Web; Update of Names from AMC to PECCBM
TS050 | Validate Names from AMC to PECCBM in Value Added Service Tab; Modify Service; Individual | Change in names from AMC to PECCBM should be validated. |  |  |  | Menard
TS050 | TC070_Validate names from AMC to PECCBM; Modify Service; Individual | changes in names should be validated. |  | Passed
TS051 | Validate Names from AMC to PECCBM in Value Added Service Tab; Modify Service; Business | Change in names from AMC to PECCBM should be validated. |  |  |  | Menard
TS051 | TC071_Validate names from AMC to PECCBM; Modify Service; Business | changes in names should be validated. |  | Passed
TS052 | Validate Names from AMC to PECCBM in Value Added Service Tab; Reactivate Service; Individual | Change in names from AMC to PECCBM should be validated. |  |  |  | Menard
TS052 | TC072_Validate names from AMC to PECCBM; Reactivate Service; Individual | changes in names should be validated. |  | Passed
TS053 | Validate Names from AMC to PECCBM in Value Added Service Tab; Reactivate Service; Business | Change in names from AMC to PECCBM should be validated. |  |  |  | Menard
| TC073_Validate names from AMC to PECCBM; Reactivate Service; Business | changes in names should be validated. |  | Passed
Implementing CBM Updates; Web; FAQs Page Update
TS054 | Validate FAQs Page Update of CBM to PECCBM; Meralco Online | FAQs Page Update should be validated.
| TC074_Validate CBM Projects Interim Process in FAQs Page | FAQs Page Update should be validated; Changes in description should be validated. |  | Deferred
Bills and Payment - Updated Payment Confirmation Template
TS055 | Validation of Payment Confirmation_Meralco Online | Payment transaction should be successful |  |  |  | Menard
| TC077_Payment Transaction | Payment transaction should be successful |  | Passed |  | RETESTED
| TC078_Payment Confirmation Validation | Payment Confirmation should be validated. |  | Passed |  | CTS-203
TS056 | Validation of Payment Confirmation_Android | Payment transaction should be successful |  |  |  | Melvene
| TC077_Payment Transaction | Payment transaction should be successful |  | Passed |  | Retest - CTS-205 / CTS 215 | Bayad - Unable to input card number and CVV/CVC
| TC078_Payment Confirmation Validation | Payment Confirmation should be validated. |  | Passed |  | Retest - CTS-205 / CTS 215 | Bayad - Unable to input card number and CVV/CVC
TS057 | Validation of Payment Confirmation_iOS | Payment transaction should be successful |  |  |  | Menard
| TC077_Payment Transaction | Payment transaction should be successful |  | DEFERRED
| TC078_Payment Confirmation Validation | Payment Confirmation should be validated. |  | DEFERRED |  | CTS-216
Appsflyer and SDK Tracking
TS058 | Validation of appsflyer tracking after SDK Upgrade | Appsflyer should be validated. |  |  |  | Menard
Precondition | SDK version should be validated; Payment Transaction should have been made; An Outage report was created; A service has been enrolled for paperless billing; A new MO registration should be process
| TC080_Validate appsflyer tracking after SDK upgrade | Appsflyer should be validated. |  | PASSED
Outage - Mobile App
TS059 | Create Outage Report_No Power - My house/building only; Android | Outage report should be created. Reference number should be generated. |  |  |  | Melvene
| TC081_Creation of Outage Report_Mobile App | Outage report should be created. Reference number should be generated. |  | Passed
TS060 | Create Outage Report_No Power - Whole street/block; Android | Outage report should be created. Reference number should be generated. |  |  |  | Melvene
| TC081_Creation of Outage Report_Mobile App | Outage report should be created. Reference number should be generated. |  | Passed
TS061 | Create Outage Report_No Power - Unstable Power; Android | Outage report should be created. Reference number should be generated. |  |  |  | Melvene
| TC081_Creation of Outage Report_Mobile App | Outage report should be created. Reference number should be generated. |  | Passed
TS062 | Create Outage Report_No Power - Streetlight Concern; Android | Outage report should be created. Reference number should be generated. |  |  |  | Melvene
| TC081_Creation of Outage Report_Mobile App | Outage report should be created. Reference number should be generated. |  | Passed
TS063 | Create Outage Report_No Power - Safety Concern; Android | Outage report should be created. Reference number should be generated. |  |  |  | Melvene
| TC081_Creation of Outage Report_Mobile App | Outage report should be created. Reference number should be generated. |  | Passed
TS064 | Create Outage Report_No Power - My house/building only; iOS | Outage report should be created. Reference number should be generated. |  |  |  | Menard
| TC081_Creation of Outage Report_Mobile App | Outage report should be created. Reference number should be generated. |  | Passed
TS065 | Create Outage Report_No Power - Whole street/block; iOS | Outage report should be created. Reference number should be generated. |  |  |  | Menard
| TC081_Creation of Outage Report_Mobile App | Outage report should be created. Reference number should be generated. |  | Passed
TS066 | Create Outage Report_No Power - Unstable Power; iOS | Outage report should be created. Reference number should be generated. |  |  |  | Menard
| TC081_Creation of Outage Report_Mobile App | Outage report should be created. Reference number should be generated. |  | Passed
TS067 | Create Outage Report_No Power - Streetlight Concern; iOS | Outage report should be created. Reference number should be generated. |  |  |  | Menard
| TC081_Creation of Outage Report_Mobile App | Outage report should be created. Reference number should be generated. |  | Passed
TS068 | Create Outage Report_No Power - Safety Concern; iOS | Outage report should be created. Reference number should be generated. |  |  |  | Menard
| TC081_Creation of Outage Report_Mobile App | Outage report should be created. Reference number should be generated. |  | Passed
Paperless Billing
TS069 | Subscribe to Paperless Billing_Meralco Online | Subscription to Paperless Billing should be successful |  |  |  | Melvene
| TC082_Subscribe to Paperless Billing_Meralco Online | Subscription to Paperless Billing should be successful |  | Passed
TS070 | Unsubscribe from Paperless Billing_Meralco Online | Cancellation of Paperless Billing should be successful |  |  |  | Melvene
Precondition | Account should be subscribed to Paperless Billing for atleast 6 months
| TC083_Unsubscribe from Paperless Billing _Meralco Online | Cancellation of Paperless Billing should be successful |  | Passed
TS071 | Subscribe to Paperless Billing_Android | Account should be subscribed to Paperless Billing |  |  |  | Menard
| TC084_Subscribe to Paperless Billing_Mobile App | Account should be subscribed to Paperless Billing |  | Passed
TS072 | Unsubscribe from Paperless Billing_Android | Account should be unsubscribed from Paperless Billing |  |  |  | Menard
Precondition | Account should be subscribed to Paperless Billing for atleast 6 months
| TC085_Unsubscribe from Paperless Billing_Mobile App | Account should be unsubscribed from Paperless Billing |  | Passed
TS073 | Subscribe to Paperless Billing_iOS | Account should be subscribed to Paperless Billing |  |  |  | Menard
Precondition | Account should not be subscribed to Paperless Billing
| TC084_Subscribe to Paperless Billing_Mobile App | Account should be subscribed to Paperless Billing |  | Passed
TS074 | Unsubscribe from Paperless Billing_iOS | Account should be unsubscribed from Paperless Billing |  |  |  | Menard
Precondition | Account should be subscribed to Paperless Billing for at least 6 months
| TC085_Unsubscribe from Paperless Billing_Mobile App | Account should be unsubscribed from Paperless Billing |  | Passed
Account Management and Payments; Registration_Regular
TS075 | MO Registration; Regular Account; Android | User should be able to register. |  |  |  | Menard
| TC086_Regular Registration; Mobile App | User should be able to register. |  | Passed
TS076 | MO Registration; Regular Account; iOS | User should be able to register. |  |  |  | Menard
| TC086_Regular Registration; Mobile App | User should be able to register. |  | Passed
Outage - Fix production issue: Redirection to FAQ from Outage Map
TS077 | Validation of Redirection to FAQs Landing Page from Outage Map | FAQs Landing Page redirection from Outage Map |  |  |  | Menard
| TC087_Validate Redirection to FAQs Landing Page | User should be redirected to FAQ Landing Page |  | Passed
Others - Update UI of Inactivity Prompt for Web
TS078 | Validation of Inactivity Prompt; Meralco Online | Inactivity Prompt should be validated. |  |  |  | Menard
Precondition | User should not do any transaction in MO for 30 seconds.
| TC088_Validate Inactivity Prompt | Inactivity Prompt should be validated. |  | Passed
Service Application - Implementing CBM Updates; Web; Link Out to PECCBM Platform
TS079 | Validate Link Out to PECCBM Flatform from MO; Individual_Registered User | Link out to PECCBM Flatform from MO should be validated. |  |  |  | Menard
| TC089_Validate Popup Window for PECCBM in Start Service; Yes_Registered | User should be redirected to the PECCBM Platform Customer Landing Page. |  | Passed
| TC090_Validate Popup Window for PECCBM in Start Service; No_Registered | User should be redirected to Start A Service Page. |  | Passed
TS080 | Validate Link Out to PECCBM Flatform from MO; Business_Registered User | Link out to PECCBM Flatform from MO should be validated. |  |  |  | Menard
| TC089_Validate Popup Window for PECCBM in Start Service; Yes_Registered | User should be redirected to the PECCBM Platform Customer Landing Page. |  | Passed
| TC090_Validate Popup Window for PECCBM in Start Service; No_Registered | User should be redirected to Start A Service Page. |  | Passed
Implement CBM Updated - FAQs Page Update
TS081 | Validate PECCBM Updates in FAQs Pages | FAQs Pages should be validated.
| TC091_Validate FAQs Updates in Service Phases: 1-Phase and 3-Phase Page | FAQs Page should be validated. |  | Deferred
| TC092_Validate FAQs Updates in Sub-Meter Requests Page | FAQs Page should be validated. |  | Deferred
| TC093_Validate FAQs Updates in New Connection for Residential Page | FAQs Page should be validated. |  | Deferred
| TC094_Validate FAQs Updates in Voltage Requirements for Residential Services Page | FAQs Page should be validated. |  | Deferred
| TC095_Validate FAQs Updates in Electrical Experts Certified by Meralco (CBM) Page | FAQs Page should be validated. |  | Deferred
| TC096_Validate FAQs Updates in AMC Services & Other Contractors Page | FAQs Page should be validated. |  | Deferred
Service Application - Captcha; Registered User
TS082 | New Service Application; Registered User; Individual_Validation of Captcha | Captcha should be validated. |  |  |  | Menard
Precondition | Account should be Individual.
| TC097_Create New Service Application in MO | Service Request should be successful; Captcha should be validated. |  | PASSED
| TC061_Validate Case Number in CXE | Case Number should be validated in CXE. |  | PASSED
TS083 | New Service Application; Registered User; Business_Validation of Captcha | Captcha should be validated. |  |  |  | Melvene
Precondition | Account should be Business.
| TC097_Create New Service Application in MO | Service Request should be successful; Captcha should be validated. |  | PASSED
| TC061_Validate Case Number in CXE | Case Number should be validated in CXE. |  | PASSED
TS084 | Modification of Electric Service; Registered User; Individual_Validation of Captcha | Captcha should be validated. |  |  |  | Melvene
Precondition | Service should be active
| TC098_Modification of Electric Service in MO | Service Request should be successful; Captcha should be validated. |  | PASSED
| TC061_Validate Case Number in CXE | Case Number should be validated in CXE. |  | PASSED
TS085 | Modification of Electric Service; Registered User; Business_Validation of Captcha | Captcha should be validated. |  |  |  | Melvene
Precondition | Service should be active. Service should be Business.
| TC098_Modification of Electric Service in MO | Service Request should be successful; Captcha should be validated. |  | PASSED
| TC061_Validate Case Number in CXE | Case Number should be validated in CXE. |  | PASSED
TS086 | Termination of Electric Service; Registered User; Individual_Validation of Captcha | Captcha should be validated. |  |  |  | Melvene
Precondition | Service should be active.
| TC099_Termination of Electric Service in MO | Service Request should be successful; Captcha should be validated. |  | PASSED |  | Retested due to issue CTS-213
| TC061_Validate Case Number in CXE | Case Number should be validated in CXE. |  | PASSED |  | Retested due to issue CTS-213
TS087 | Termination of Electric Service; Registered User; Business_Validation of Captcha | Captcha should be validated. |  |  |  | Melvene
Precondition | Service should be active. Service should be Business.
| TC099_Termination of Electric Service in MO | Service Request should be successful; Captcha should be validated. |  | PASSED
| TC061_Validate Case Number in CXE | Case Number should be validated in CXE. |  | PASSED
TS088 | Recontract of Electric Service; Registered User; Individual_Validation of Captcha | Captcha should be validated. |  |  |  | Melvene
Precondition | Service should be Terminated.
| TC100_Recontract of Electric Service in MO | Service Request should be successful; Captcha should be validated. |  | PASSED |  | Multiple Retest due to bad data.
| TC061_Validate Case Number in CXE | Case Number should be validated in CXE. |  | PASSED
TS089 | Recontract of Electric Service; Registered User; Business_Validation of Captcha | Captcha should be validated. |  |  |  | Melvene
Precondition | Service should be Terminated. Service should be Business.
| TC100_Recontract of Electric Service in MO | Service Request should be successful; Captcha should be validated. |  | PASSED
| TC061_Validate Case Number in CXE | Case Number should be validated in CXE. |  | PASSED
147

## AT - Test Case
Test Case Description (Description of the test) | Step Name | Description | Expected Result | Status | Remarks
TC001_Validate SSO login with Service Enrollment w/o Mobile Number; Meralco Online_Facebook
| 1 | Go to Meralco Online | User should be directed to login Page.
| 2 | Sign In SSO Account via Facebook | Prompt should be displayed.
| 3 | Populate field for Mobile Number > Submit | User should successfully login.
TC002_Validate SSO login with Service Enrollment w/o Mobile Number; Meralco Online_Google
| 1 | Go to Meralco Online | User should be directed to login Page.
| 2 | Sign In SSO Account via Google | Prompt should be displayed.
| 3 | Populate field for Mobile Number > Submit | User should successfully login.
TC003_Validate SSO login with Service Enrollment w/o Mobile Number; Meralco Online_Apple ID
| 1 | Go to Meralco Online | User should be directed to login Page.
| 2 | Sign In SSO Account via Apple ID | Prompt should be displayed.
| 3 | Populate field for Mobile Number > Submit | User should successfully login.
TC004_Validate SSO login w/o Mobile Number and Service Enrollment; Meralco Online_Facebook
| 1 | Go to Meralco Online | User should be directed to login Page.
| 2 | Sign In SSO Account via Facebook | Prompt should be displayed.
| 3 | Populate required fields > Submit | User should successfully login.
TC005_Validate SSO login w/o Mobile Number and Service Enrollment; Meralco Online_Google
| 1 | Go to Meralco Online | User should be directed to login Page.
| 2 | Sign In SSO Account via Google | Prompt should be displayed.
| 3 | Populate required fields > Submit | User should successfully login.
TC006_Validate SSO login w/o Mobile Number and Service Enrollment; Meralco Online_Apple ID
| 1 | Go to Meralco Online | User should be directed to login Page.
| 2 | Sign In SSO Account via Apple ID | Prompt should be displayed.
| 3 | Populate required fields > Submit | User should successfully login.
TC007_Validate SSO login with Mobile Number; Meralco Online_Facebook
| 1 | Go to Meralco Online | User should be directed to login Page.
| 2 | Sign In SSO Account via Facebook | Prompt should be displayed.
| 3 | Populate required fields except for Service Enrollment > Submit | User should successfully login.
TC008_Validate SSO login with Mobile Number; Meralco Online_Google
| 1 | Go to Meralco Online | User should be directed to login Page.
| 2 | Sign In SSO Account via Google | Prompt should be displayed.
| 3 | Populate Service Enrollment > Submit | User should successfully login.
TC009_Validate SSO login with Mobile Number; Meralco Online_Apple ID
| 1 | Go to Meralco Online | User should be directed to login Page.
| 2 | Sign In SSO Account via Apple ID | Prompt should be displayed.
| 3 | Populate Service Enrollment > Submit | User should successfully login.
TC010_Validate SSO login with Service Enrollment with Mobile Number; Meralco Online_Facebook
| 1 | Go to Meralco Online | User should be directed to login Page.
| 2 | Sign In SSO Account via Facebook | User should successfully login.
TC011_Validate SSO login with Service Enrollment with Mobile Number; Meralco Online_Google
| 1 | Go to Meralco Online | User should be directed to login Page.
| 2 | Sign In SSO Account via Google | User should successfully login.
TC012_Validate SSO login with Service Enrollment with Mobile Number; Meralco Online_Apple ID
| 1 | Go to Meralco Online | User should be directed to login Page.
| 2 | Sign In SSO Account via Apple ID | User should successfully login.
TC013_Validate SSO login with Service Enrollment w/o Mobile Number; Android_Facebook
| 1 | Go to Meralco Online | User should be directed to login Page.
| 2 | Sign In SSO Account via Facebook | Prompt should be displayed.
| 3 | Populate field for Mobile Number > Submit | User should successfully login.
TC014_Validate SSO login with Service Enrollment w/o Mobile Number; Android_Google
| 1 | Go to Meralco Online | User should be directed to login Page.
| 2 | Sign In SSO Account via Google | Prompt should be displayed.
| 3 | Populate field for Mobile Number > Submit | User should successfully login.
TC015_Validate SSO login w/o Mobile Number and Service Enrollment; Android_Facebook
| 1 | Go to Meralco Online | User should be directed to login Page.
| 2 | Sign In SSO Account via Facebook | Prompt should be displayed.
| 3 | Populate required fields > Submit | User should successfully login.
TC016_Validate SSO login w/o Mobile Number and Service Enrollment; Android_Google
| 1 | Go to Meralco Online | User should be directed to login Page.
| 2 | Sign In SSO Account via Google | Prompt should be displayed.
| 3 | Populate required fields > Submit | User should successfully login.
TC017_Validate SSO login with Mobile Number; Android_Facebook
| 1 | Go to Meralco Online | User should be directed to login Page.
| 2 | Sign In SSO Account via Facebook | Prompt should be displayed.
| 3 | Populate required fields except for Service Enrollment > Submit | User should successfully login.
TC018_Validate SSO login with Mobile Number; Android_Google
| 1 | Go to Meralco Online | User should be directed to login Page.
| 2 | Sign In SSO Account via Google | Prompt should be displayed.
| 3 | Populate required fields except for Service Enrollment > Submit | User should successfully login.
TC019_Validate SSO login with Service Enrollment with Mobile Number; Android_Facebook
| 1 | Go to Meralco Online | User should be directed to login Page.
| 2 | Sign In SSO Account via Facebook | User should successfully login.
TC020_Validate SSO login with Service Enrollment with Mobile Number; Android_Google
| 1 | Go to Meralco Online | User should be directed to login Page.
| 2 | Sign In SSO Account via Google | User should successfully login.
TC021_Validate SSO login with Service Enrollment w/o Mobile Number; iOS_Facebook
| 1 | Go to Meralco Online > Login Page | User should be directed to login Page.
| 2 | Sign In SSO Account via Facebook | Prompt should be displayed.
| 3 | Populate field for Mobile Number > Submit | User should successfully login.
TC022_Validate SSO login with Service Enrollment w/o Mobile Number; iOS_Google
| 1 | Go to Meralco Online > Login Page | User should be directed to login Page.
| 2 | Sign In SSO Account via Google | Prompt should be displayed.
| 3 | Populate field for Mobile Number > Submit | User should successfully login.
TC023_Validate SSO login with Service Enrollment w/o Mobile Number; iOS_Apple ID
| 1 | Go to Meralco Online | User should be directed to login Page.
| 2 | Sign In SSO Account via Apple ID | Prompt should be displayed.
| 3 | Populate field for Mobile Number and Tick Terms and Conditions > Submit | User should successfully login.
TC024_Validate SSO login w/o Mobile Number and Service Enrollment; iOS_Facebook
| 1 | Go to Meralco Online | User should be directed to login Page.
| 2 | Sign In SSO Account via Facebook | Prompt should be displayed.
| 3 | Populate required fields > Submit | User should successfully login.
TC025_Validate SSO login w/o Mobile Number and Service Enrollment; iOS_Google
| 1 | Go to Meralco Online | User should be directed to login Page.
| 2 | Sign In SSO Account via Google | Prompt should be displayed.
| 3 | Populate required fields > Submit | User should successfully login.
TC026_Validate SSO login w/o Mobile Number and Service Enrollment; iOS_Apple ID
| 1 | Go to Meralco Online > Login | User should be directed to login Page.
| 2 | Sign In SSO Account via Apple ID | Prompt should be displayed.
| 3 | Populate required fields > Submit | User should successfully login.
TC027_Validate SSO login with Mobile Number; iOS_Facebook
| 1 | Go to Meralco Online > Login | User should be directed to login Page.
| 2 | Sign In SSO Account via Facebook | Prompt should be displayed.
| 3 | Populate required fields > Submit | User should successfully login.
TC028_Validate SSO login with Mobile Number; iOS_Google
| 1 | Go to Meralco Online > Login | User should be directed to login Page.
| 2 | Sign In SSO Account via Google | Prompt should be displayed.
| 3 | Populate Service Enrollment > Submit | User should successfully login.
TC029_Validate SSO login with Mobile Number; iOS_Apple ID
| 1 | Go to Meralco Online > Login | User should be directed to login Page.
| 2 | Sign In SSO Account via Apple ID | Prompt should be displayed.
| 3 | Populate required fields > Submit | User should successfully login.
TC030_Validate SSO login with Service Enrollment with Mobile Number; iOS_Facebook
| 1 | Go to Meralco Online > Login | User should be directed to login Page.
| 2 | Sign In SSO Account via Facebook | User should successfully login.
TC031_Validate SSO login with Service Enrollment with Mobile Number; iOS_Google
| 1 | Go to Meralco Online > Login | User should be directed to login Page
| 2 | Sign In SSO Account via Google | User should successfully login.
TC032_Validate SSO login with Service Enrollment with Mobile Number; iOS_Apple ID
| 1 | Go to Meralco Online > Login | User should be directed to login Page.
| 2 | Sign In SSO Account via Apple ID | User should successfully login.
TC033_Validate Welcome Email for Apple SSO Users
| 1 | Validate welcome email notification for Apple SSO Users for the following SSO Login: * Facebook * Google * Apple ID | See Reference Tab for Template. Reference No.: 001
TC034_Validate Clear All Button in Notification Inbox_Android
| 1 | Click the Notification Bell in Upper Right Corner in Overview Page | User should be redirected to Notifications Inbox.
| 2 | Click Clear All | All notifications should be deleted; A popup message should appear; Customer should be redirected to Overview Page.; Red dot beside the Notification Bell should not appear.
TC035_Validate Clear All Button in Notification Inbox_iOS
| 1 | Click the Notification Bell in Upper Right Corner in Overview Page | User should be redirected to Notifications Inbox.
| 2 | Click Clear All | All notifications should be deleted; A popup message should appear; Customer should be redirected to Overview Page.; Red dot beside the Notification Bell should not appear.
TC036_Validate Trash Icon button in Notification Inbox_Android
| 1 | Click the Notification Bell in Upper Right Corner in Overview Page | User should be redirected to Notifications Inbox.
| 2 | Select Notification > Swipe the notification | Trash icon should appear
| 3 | Click Trash Icon button | Notification should be deleted.
| 4 | Click Back | Customer should be redirected to Overview Page.
TC037_Validate Trash Icon button in Notification Inbox_iOS
| 1 | Click the Notification Bell in Upper Right Corner in Overview Page | User should be redirected to Notifications Inbox.
| 2 | Select Notification > Swipe the notification | Trash icon should appear
| 3 | Click Trash Icon button | Notification should be deleted.
| 4 | Click Back | Customer should be redirected to Overview Page.
TC038_Validate Notification Bell in Overview Page
| 1 | Validate Notifications Bell | * If there is unread notification, red dot should appear beside the Notification Bell. * If all notifications are in read state, red dot should not appear beside the Notification Bell. * If notification is empty, red dot should not appear beside the Notification Bell.
TC039_Enroll BIZ Service in MO Account_Meralco Online
| 1 | In Meralco Online, Go to Accounts > Enroll A Service | Enroll a Service Page should be displayed.
| 2 | Populate required fields > Submit | Registration should be successful; A message should be displayed. See reference tab for Reference No.: 002
TC040_Enroll BIZ Service in MO Account_Android
| 1 | Click Hamburger Button > Click Switch or Add Service > Click Add | Add a Service Page should be displayed.
| 2 | Tick "I already have a Meralco Bill" > Populate required fields > Click Add | Registration should be successful; A message should be displayed. See reference tab for Reference No.: 002
TC041_Enroll BIZ Service in MO Account_iOS
| 1 | Click Hamburger Button > Click Switch or Add Service > Click Add | Add a Service Page should be displayed.
| 2 | Tick "I already have a Meralco Bill" > Populate required fields > Click Add | Registration should be successful; A message should be displayed. See reference tab for Reference No.: 002
TC042_Add Area Code in Landline Field_Meralco Online
| 1 | In Meralco Online, Click Username > My Profile > Navigate to Landline > Click Edit Icon | Fields should be enabled for fill out.
| 2 | Input the following in Landline: - 2-digit Area Code - 8-digit number > Click Save | Changes should be made.
TC043_Add Area Code in Landline Field_Android
| 1 | In Settings Page, Click My Profile > Click Edit | My Profile should be displayed; Fields should be enabled for fill out.
| 2 | Input the following in Landline: - 2-digit Area Code - 8-digit number > Click Save | Changes should be made; A popup message should display. "Your changes have been saved."
TC044_Add Area Code in Landline Field_iOS
| 1 | In Settings Page, Click My Profile > Click Edit | My Profile should be displayed; Fields should be enabled for fill out.
| 2 | Input the following in Landline: - 2-digit Area Code - 8-digit number > Click Save | Changes should be made; A popup message should display. "Your changes have been saved."
TC045_Exclude Area Code in Landline Field_Meralco Online
| 1 | In Meralco Online, Click Username > My Profile > Navigate to Landline > Click Edit Icon | Fields should be enabled for fill out.
| 2 | Input the following in Landline: - 8-digit number > Click Save | Changes should not be made.
TC046_Exclude Area Code in Landline Field_Android
| 1 | In Settings Page, Click My Profile > Click Edit | My Profile should be displayed; Fields should be enabled for fill out.
| 2 | Input the following in Landline: - 8-digit number > Click Save | Changes should not be made; An error message should appear.
TC047_Exclude Area Code in Landline Field_iOS
| 3 | In Settings Page, Click My Profile > Click Edit | My Profile should be displayed; Fields should be enabled for fill out.
| 4 | Input the following in Landline: - 8-digit number > Click Save | Changes should not be made; An error message should appear.
TC048_Create an Outage Report
| 1 | Go to Outages & Incidents > Report Streetlight And Safety Concerns | User should be redirected to Report an Outage or Incident Form.
| 2 | Populate required fields > click Submit | Outage report should be created. Reference number should be generated
TC049_Validate APA Unenrollment Button
| 1 | Go to Accounts > Manage Accounts | User should be redirected to Account Management Page.
| 2 | Select CAN and SIN > Navigate to Bottom of Account Management Page | CAN and SIN should be selected; Buttons are displayed; First Row: * Subscribe to Paperless Billing * Unsubscribe from Paperless Billing * Unenroll from Auto Payment Arrangements * Unenroll Electric Services Second Row: * Change Service Details * Change Contract Details * Reactivate Electric Service * Stop Electric Service
| 3 | Click Unenroll from Auto Payments Arrangements | User should be redirected to APA unenrollment form.
| 4 | Populate required fields > Submit | Unenrollment request should be successful; Reference Number should be generated.
TC050_Create New Service Application_Individual
| 1 | Go to https://fuat-meralco.cs73.force.com/customers/s/cxe-apply | Service Application page should be displayed
| 2 | Click on Individual | The following should be displayed under Individual - Start Service - Modify Service - Reactivate Service - Stop Service
| 3 | Click on Start a Service | A popup message should be displayed.
| 4 | Click No | User should be redirected to MO Create a New Account Page.
| 5 | Populate the following: - Email - First Name - Middle Name (Optional) - Last Name - Mobile Number > Tick Terms and Condition > Click Register | Confirmation message; "We've sent you a confirmation email. Please click on the link to proceed with your registration." "If you can't find the confirmation email in your inbox, please check your spam folder." should be displayed
| 6 | Access the email account used for the registration | Meralco Online Email Verification should be in the email's inbox
| 7 | Open Online Email Verification email > Click on here hyperlink | User should be directed to Set Password page
| 8 | Set Password then login | Password should be set; User should be directed to Overview page
| 9 | Click on Request for a Service tile | A popup message should be displayed.
| 10 | Click No | Start a Service page should be displayed
| 11 | Populate all required fields in Contact Information tab > Click Next | Fields should be populated; New Address tab should be displayed
| 12 | Populate the following: Service Address Province City / Municipality Home Ownership Billing Address Indicator | Fields should be populated; Value Added Service tab should be displayed
| 13 | Populate the following: Notification indicator Paperless Billing indicator APA indicator > Attach documents > Click Next | Fields should be populated; Terms and Conditions tab should be displayed
| 14 | Tick on I have read and agree to the Meralco Online Terms & Conditions and consent to the processing of my personal data in accordance with the Privacy Policy | Should be able to tick checkbox
| 15 | Click on captcha | Should be able to verify captcha; Submit button should be enabled
| 16 | Click Submit | Confirmation tab should be displayed. Case # should be generated.
TC051_Create New Service Application_Business
| 1 | Go to https://fuat-meralco.cs73.force.com/customers/s/cxe-apply | Service Application page should be displayed
| 2 | Click on Business | The following should be displayed under Business - Start Service - Modify Service - Reactivate Service - Stop Service
| 3 | Click on Start a Service | A popup window should be displayed
| 4 | Click No | User should be directed to Start a Service Page.
| 5 | Populate the following fields: - Company Name - Trade Name (Optional) - Company Email Address (Optional) - Company Landline - First Name - Last Name - Email Address - Mobile Number - Designation > Click Next | Fields should be populated; New Address tab should be displayed
| 6 | Populate the following: Service Address Province City / Municipality Home Ownership Billing Address Indicator > Click Next | Fields should be populated; Value Added Service tab should be displayed
| 7 | Populate the following: Notification indicator > Attach documents > Click Next | Fields should be populated; Terms and Conditions tab should be displayed
| 8 | Tick on I have read and agree to the Meralco Online Terms & Conditions and consent to the processing of my personal data in accordance with the Privacy Policy | Should be able to tick checkbox
| 9 | Click on Captcha | Should be able to verify captcha; Submit button should be enabled
| 10 | Click Submit | Confirmation tab should be displayed. Case # should be generated.
TC052_Create New Service Application_Contractor
| 1 | Go to https://fuat-meralco.cs73.force.com/customers/s/cxe-apply | Service Application page should be displayed
| 2 | Click on Contractor | The following should be displayed under Contractor - Start Service - Modify Service - Reactivate Service - Stop Service
| 3 | Click on Start a Service | A popup message should be displayed.
| 4 | Select Contrator > Click Submit | Start a Service page should be displayed
| 5 | Populate the following fields: First Name* Last Name* Business Name* Email Address* Mobile Number* Relationship to Customer* Notification indicator | Fields should be populated; Customer Info tab should be displayed
| 6 | Populate the following: Electric Service indicator* First Name* Middle Name Last Name* Email Address* Birthday* Mobile Number* Landline > Click Next | Fields should be populated; New Address tab should be displayed
| 7 | Populate the following: Service Address Province City / Municipality Home Ownership Billing Address Indicator > Attach Document > Click Next | Fields should be populated; Terms and Conditions tab should be displayed
| 8 | Tick on I have read and agree to the Meralco Online Terms & Conditions and consent to the processing of my personal data in accordance with the Privacy Policy | Should be able to tick checkbox
| 9 | Click on Captcha | Should be able to verify captcha; Next button should be enabled
| 10 | Click Next | Confirmation tab should be displayed. Case # should be generated.
TC053_Modification of Electric Service_Individual
| 1 | Go tohttps://fuat-meralco.cs73.force.com/customers/s/cxe-apply | Service Application page should be displayed
| 2 | Click on Individual | The following should be displayed under Business - Start Service - Modify Service - Reactivate Service - Stop Service
| 3 | Click on Modify Service | Request page for Modify Service should be displayed
| 4 | Populate CAN field and SIN field | CAN and SIN field should be populated
| 5 | Tick Change my Contract Details then tick Change in Contract Name | Change in Contract Name should be selected
| 6 | Populate the following First Name* Middle Name Last Name* Email Address* Mobile Number* Landline Number > Click Next | Fields should be populated; Contact Information tab should be displayed
| 7 | Populate the following field: First Name* Middle Name Last Name* Email Address* Mobile Number* Relation to Customer > Click Next | Fields should be populated; Value Added Service tab should be displayed
| 8 | Populate the following: Notification indicator PECCBM indicator > Attach documents > Click Next | Fields should be populated; Terms and Conditions tab should be displayed
| 8 | Tick on I have read and agree to the Meralco Online Terms & Conditions and consent to the processing of my personal data in accordance with the Privacy Policy | Should be able to tick checkbox
| 9 | Click on Captcha | Should be able to verify captcha; Next button should be enabled
| 10 | Click Submit | Confirmation tab should be displayed. Case # should be generated.
TC054_Modification of Electric Service_Business
| 1 | Go to https://fuat-meralco.cs73.force.com/customers/s/cxe-apply | Service Application page should be displayed
| 2 | Click on Business | The following should be displayed under Business - Start Service - Modify Service - Reactivate Service - Stop Service
| 3 | Click on Modify Service | Request page for Modify Service should be displayed
| 4 | Populate CAN field | CAN field should be populated
| 5 | Tick Change my Contract Details then tick Transfer of Service | Transfer of Service should be selected
| 6 | Populate the following Company Name* Doing Business As Business Email Address Business Landline* First Name* Last Name* Email Address* Mobile Number* Designation* > Click Next | Fields should be populated; Contact Information tab should be displayed
| 7 | Populate the following field: First Name* Middle Name Last Name* Email Address* Mobile Number* > Click Next | Fields should be populated; Value Added Service tab should be displayed
| 8 | Populate the following: Notification indicator PECCBM indicator > Attach documents > Click Next | Fields should be populated; Terms and Conditions tab should be displayed
| 9 | Tick on Terms & Conditions and Privacy Policy agreement | Should be able to tick checkbox
| 10 | Click on Captcha | Should be able to verify captcha; Submit button should be enabled
| 11 | Click Submit | Confirmation tab should be displayed. Case # should be generated.
TC055_Modification of Electric Service_Contractor
| 1 | Go to https://fuat-meralco.cs73.force.com/customers/s/cxe-apply | Service Application page should be displayed
| 2 | Click on Contractor | The following should be displayed under Contractor - Start Service - Modify Service - Reactivate Service - Stop Service
| 3 | Click on Modify Service | Request page for Modify Service should be displayed
| 4 | Populate CAN field | CAN field should be populated
| 5 | Tick Change my Service Details > tick Request to downgrade electrical load > Click Next | Request to downgrade electrical should be selected; Contractor Info tab should be displayed
| 6 | Populate the following field: First Name* Last Name* Business Name Email Address* Mobile Number* Relation to Customer Attach Documents > Click Next | Fields should be populated; Terms and Conditions tab should be displayed
| 7 | Tick on I have read and agree to the Meralco Online Terms & Conditions and consent to the processing of my personal data in accordance with the Privacy Policy | Should be able to tick checkbox
| 8 | Click on Captcha | Should be able to verify captcha; Next button should be enabled
| 9 | Click Next | Confirmation tab should be displayed. Case # should be generated.
TC056_Termination of Electric Service_Individual
| 1 | Go to https://fuat-meralco.cs73.force.com/customers/s/cxe-apply | Service Application page should be displayed
| 2 | Click on Individual | The following should be displayed under Individual - Start Service - Modify Service - Reactivate Service - Stop Service
| 3 | Select Stop Service | Stop Service page should be displayed
| 4 | Populate CAN field | CAN field should be populated
| 5 | Populate the following: First Name* Middle Name Last Name* Email Address* Mobile Number* Relation to Customer > Attach Documents > Click Next | Fields should be populated; Terms and Conditions tab should be displayed
| 6 | Tick on I have read and agree to the Meralco Online Terms & Conditions and consent to the processing of my personal data in accordance with the Privacy Policy | Should be able to tick checkbox
| 7 | Click on Captcha | Should be able to verify captcha; Next button should be enabled
| 8 | Click Submit | Confirmation tab should be displayed. Case # should be generated.
TC057_Termination of Electric Service_Business
| 1 | Go tohttps://fuat-meralco.cs73.force.com/customers/s/cxe-apply | Service Application page should be displayed
| 2 | Click on Business | The following should be displayed under Business - Start Service - Modify Service - Reactivate Service - Stop Service
| 3 | Select Stop Electric Service | Stop Electric Service page should be displayed
| 4 | Populate CAN field | CAN field should be populated
| 5 | Populate the following: First Name* Middle Name Last Name* Email Address* Mobile Number* Designation > Attach Documents > Click Next | Fields should be populated; Terms and Conditions tab should be displayed
| 6 | Tick on Terms & Conditions and Privacy Policy agreement > Click on Captcha | Submit button should be enabled; Captcha should be validated.
| 7 | Click Submit | Confirmation tab should be displayed. Case # should be generated.
TC058_Termination of Electric Service_Contractor
| 1 | Go tohttps://fuat-meralco.cs73.force.com/customers/s/cxe-apply | Service Application page should be displayed
| 2 | Click on Contractor | The following should be displayed under Contractor - Start Service - Modify Service - Reactivate Service - Stop Service
| 3 | Select Stop Electric Service | Stop a Service page should be displayed.
| 4 | Populate CAN field | CAN field should be populated
| 5 | Populate the following: First Name* Last Name* Business Name* Email Address* Mobile Number* Relationship to Customer* Notification indicator > Click Next | Fields should be populated; Terms and Conditions tab should be displayed
| 6 | Tick on Terms & Conditions and Privacy Policy agreement > Click on Captcha | Submit button should be enabled; Captcha should be validated.
| 7 | Click Submit | Confirmation tab should be displayed. Case # should be generated.
TC059_Recontract of Electric Service_Business
| 1 | Go tohttps://fuat-meralco.cs73.force.com/customers/s/cxe-apply | Service Application page should be displayed
| 2 | Click on Business | The following should be displayed under Business - Start Service - Modify Service - Reactivate Service - Stop Service
| 3 | Click on Reactivate Service | Reactivate a Service page should be displayed
| 4 | Populate CAN field | CAN field should be populated
| 5 | Populate the following fields: - Company Name - Trade Name (Optional) - Company Email Address (Optional) - Company Landline - First Name - Last Name - Email Address - Mobile Number - Designation > Click Next | Fields should be populated; Value Added Service tab should be displayed
| 6 | Populate the following: Notification indicator PECCBM indicator > Attach documents > Click Next | Fields should be populated; Terms and Conditions tab should be displayed
| 7 | Tick on Terms & Conditions and Privacy Policy agreement > Click on Captcha | Submit button should be enabled; Captcha should be validated.
| 8 | Click Submit | Confirmation tab should be displayed. Case # should be generated.
TC060_Recontract of Electric Service_Contractor
| 1 | Go to https://fuat-meralco.cs73.force.com/customers/s/cxe-apply | Service Application page should be displayed
| 2 | Click on Contractor | The following should be displayed under Contractor - Start Service - Modify Service - Reactivate Service - Stop Service
| 3 | Click on Reactivate Service > Populate all required fields in Contractor Info > Click Next | Customer Info tab should be displayed
| 4 | Populate fields in Customer Info | Fields should be populated.
| 5 | In New Address Tab Click Next | Terms and Conditions tab should be displayed
| 6 | Tick on Terms & Conditions and Privacy Policy agreement > Click on Captcha | Next button should be enabled; Captcha should be validated.
| 7 | Click Next | Confirmation tab should be displayed. Case # should be generated.
TC061_Validate Case Number in CXE
| 1 | In CXE, Go to Cases > Search Case Number | Case should be searched and validated.
TC062_Validate Popup Window for PECCBM in Start A Service via CXE-Apply; Yes_Individual
| 1 | Go to https://fuat-meralco.cs73.force.com/customers/s/cxe-apply | Service Application page should be displayed
| 2 | Click on Individual | The following should be displayed under Contractor - Start Service - Modify Service - Reactivate Service - Stop Service
| 3 | Click Start Service | A popup should display.
| 4 | Validate Popup Message | Please See Reference Tab; Reference No.: 004
| 5 | Click Yes | User should be redirected to PECCBM Customer Landing Page.
TC063_Validate Popup Window for PECCBM in Start A Service via CXE-Apply; No_Individual
| 1 | Go to https://fuat-meralco.cs73.force.com/customers/s/cxe-apply | Service Application page should be displayed
| 2 | Click on Individual | The following should be displayed under Contractor - Start Service - Modify Service - Reactivate Service - Stop Service
| 3 | Click Start Service | A popup should display.
| 4 | Validate Popup Message | Please See Reference Tab; Reference No.: 004
| 5 | Click No | User should be redirected to the MO Create Account Page.
TC064_Validate Popup Window for PECCBM in Start A Service via CXE-Apply; Yes_Business
| 1 | Go to https://fuat-meralco.cs73.force.com/customers/s/cxe-apply | Service Application page should be displayed
| 2 | Click on Business | The following should be displayed under Contractor - Start Service - Modify Service - Reactivate Service - Stop Service
| 3 | Click Start Service | A popup should display.
| 4 | Validate Popup Message | Please See Reference Tab; Reference No.: 004
| 5 | Click Yes | User should be redirected to PECCBM Customer Landing Page.
TC065_Validate Popup Window for PECCBM in Start A Service via CXE-Apply; No_Business
| 1 | Go to https://fuat-meralco.cs73.force.com/customers/s/cxe-apply | Service Application page should be displayed
| 2 | Click on Business | The following should be displayed under Contractor - Start Service - Modify Service - Reactivate Service - Stop Service
| 3 | Click Start Service | A popup should display.
| 4 | Validate Popup Message | Please See Reference Tab; Reference No.: 004
| 5 | Click No | Business Customer should be redirected to the Start a Service Page - Contact Information in MO
TC066_Validate Popup Window for PECCBM in Start A Service via CXE-Apply; PECCBM_Contractor
| 1 | Go to https://fuat-meralco.cs73.force.com/customers/s/cxe-apply | Service Application page should be displayed
| 2 | Click on Contractor | The following should be displayed under Contractor - Start Service - Modify Service - Reactivate Service - Stop Service
| 3 | Click Start Service | A popup should display.
| 4 | Validate Popup Message | Please See Reference Tab; Reference No.: 005
| 5 | Click "Private Electrical Contractor Certified by Meralco (PECCBM)" | PECCBM Contractor should be linked out to the PECCBM Contractor Login Page.
TC067_Validate Popup Window for PECCBM in Start A Service via CXE-Apply; Contractor_Contractor
| 1 | Go to https://fuat-meralco.cs73.force.com/customers/s/cxe-apply | Service Application page should be displayed
| 2 | Click on Contractor | The following should be displayed under Contractor - Start Service - Modify Service - Reactivate Service - Stop Service
| 3 | Click Start Service | A popup should display.
| 4 | Validate Popup Message | Please See Reference Tab; Reference No.: 005
| 5 | Click "Contractor" | Contractor User should be redirected to the Start a Service Page - Contact Information in MO
TC068_Validate AMC Availment in Value Added Services Tab; Individual
| 1 | Go to https://fuat-meralco.cs73.force.com/customers/s/cxe-apply | Service Application page should be displayed
| 2 | Click on Individual | The following should be displayed under Individual - Start Service - Modify Service - Reactivate Service - Stop Service
| 3 | Click on Start a Service > Click No | MO Create a New Account should be displayed.
| 4 | Populate the following: - Email - First Name - Middle Name (Optional) - Last Name - Mobile Number > Tick Terms and Condition > Click Register | Confirmation message; "We've sent you a confirmation email. Please click on the link to proceed with your registration." "If you can't find the confirmation email in your inbox, please check your spam folder." should be displayed
| 5 | Access the email > Click on Hyperlink > Set Password and Login | Password should be set; User should be directed to Overview page
| 6 | Click on Request for a Service tile > Click No | Start a Service page should be displayed
| 7 | Populate all required fields in Contact Information tab > Click Next | Fields should be populated; New Address tab should be displayed
| 8 | Populate the following: Service Address Province City / Municipality Home Ownership Billing Address Indicator | Fields should be populated; Value Added Service tab should be displayed
| 9 | Validate AMC Availment in Value Added Service Tab | AMC Availament and Question to Customers “Do you want to have an Accredited Meralco Contractor (AMC) help you process your application?” Should be removed.
| 10 | Populate the following: Notification indicator Paperless Billing indicator APA indicator > Click Next | Fields should be populated; Terms and Conditions tab should be displayed
| 11 | Tick on I have read and agree to the Meralco Online Terms & Conditions and consent to the processing of my personal data in accordance with the Privacy Policy | Submit button should be enabled
| 12 | Click on Captcha | Captcha should be validated.
| 13 | Click Submit | Confirmation tab should be displayed. Case # should be generated.
TC069_Validate AMC Availment in Value Added Services Tab; Business
| 1 | Go tohttps://fuat-meralco.cs73.force.com/customers/s/cxe-apply | Service Application page should be displayed
| 2 | Click on Business | The following should be displayed under Business - Start Service - Modify Service - Reactivate Service - Stop Service
| 3 | Click on Start a Service > Click No | Start a Service page should be displayed
| 4 | Populate the following fields: - Company Name - Trade Name (Optional) - Company Email Address (Optional) - Company Landline - First Name - Last Name - Email Address - Mobile Number - Designation > Click Next | Fields should be populated; New Address tab should be displayed
| 5 | Populate the following: Service Address Province City / Municipality Home Ownership Billing Address Indicator > Click Next | Fields should be populated; Value Added Service tab should be displayed
| 6 | Validate AMC Availment in Value Added Service Tab | AMC Availment and Question to Customers “Do you want to have an Accredited Meralco Contractor (AMC) help you process your application?” Should be removed.
| 7 | Populate the following: Notification indicator > Click Next | Fields should be populated; Terms and Conditions tab should be displayed
| 8 | Tick on I have read and agree to the Meralco Online Terms & Conditions and consent to the processing of my personal data in accordance with the Privacy Policy | Submit button should be enabled
| 9 | Click on Captcha | Captcha should be validated.
| 10 | Click Submit | Confirmation tab should be displayed. Case # should be generated.
TC070_Validate names from AMC to PECCBM; Modify Service; Individual
| 1 | Go tohttps://fuat-meralco.cs73.force.com/customers/s/cxe-apply | Service Application page should be displayed
| 2 | Click on Individual | The following should be displayed under Business - Start Service - Modify Service - Reactivate Service - Stop Service
| 3 | Click on Modify Service > Populate CAN and SIN field | Request page for Modify Service should be displayed; CAN and SIN field should be populated
| 4 | Tick Change my Service Details > Tick Additional Load > Click Next | Change my Service Details; Additional Load should be selected; Contact Information tab should be displayed
| 5 | Populate the following field: First Name* Middle Name Last Name* Email Address* Mobile Number* Relation to Customer > Click Next | Fields should be populated; Value Added Service tab should be displayed
| 6 | Validate AMC names updated to "PECCBM" and the description of more information icon | Please refer to Reference Tab; Reference No.: 0006
TC071_Validate names from AMC to PECCBM; Modify Service; Business
| 1 | Go to https://fuat-meralco.cs73.force.com/customers/s/cxe-apply | Service Application page should be displayed
| 2 | Click on Business | The following should be displayed under Business - Start Service - Modify Service - Reactivate Service - Stop Service
| 3 | Click on Modify Service > Populate CAN and SIN field | Request page for Modify Service should be displayed; CAN and SIN field should be populated
| 4 | Tick Change my Service Details > Tick Additional Load > Click Next | Change my Service Details; Additional Load should be selected; Contact Information tab should be displayed
| 5 | Populate the following field: First Name* Middle Name Last Name* Email Address* Mobile Number* Relation to Customer > Click Next | Fields should be populated; Value Added Service tab should be displayed
| 6 | Validate AMC names updated to "PECCBM" and the description of more information icon | Please refer to Reference Tab; Reference No.: 006
TC072_Validate names from AMC to PECCBM; Reactivate Service; Individual
| 1 | Login to Meralco Online | User should be logged in to Meralco Online
| 2 | Go to Accounts > Manage Accounts | Accounts page should be displayed
| 3 | Select Account > Click Reactivate Electric Service button | Request page for Reactivate Electric Service should be displayed
| 4 | Populate the following: SIN First Name Middle Name (Optional) Last Name Email Address Mobile Number (optional) Landline (optional) Birthday (optional) Representative indicator > Click Next | Fields should be populated; New Address tab should be displayed
| 5 | Populate the following: Service Address Province City / Municipality Home Ownership Billing Address Indicator | Fields should be populated; Value Added Service tab should be displayed
| 6 | Validate AMC names updated to "PECCBM" and the description of more information icon | Please refer to Reference Tab; Reference No.: 006
TC073_Validate names from AMC to PECCBM; Reactivate Service; Business
| 1 | Go tohttps://fuat-meralco.cs73.force.com/customers/s/cxe-apply | Service Application page should be displayed
| 2 | Click on Business | The following should be displayed under Business - Start Service - Modify Service - Reactivate Service - Stop Service
| 3 | Click on Reactivate Service | Reactivate a Service page should be displayed
| 4 | Populate CAN field | CAN field should be populated
| 5 | Populate the following fields: - Company Name - Trade Name (Optional) - Company Email Address (Optional) - Company Landline - First Name - Last Name - Email Address - Mobile Number - Designation > Click Next | Fields should be populated; Value Added Service tab should be displayed
| 6 | Validate AMC names updated to "PECCBM" and the description of more information icon | Please refer to Reference Tab; Reference No.: 006
TC074_Validate FAQs Page
| 1 | Go to FAQs Page and validate the updates. | See FAQs Template File for reference; Reference: Requirement No.: 2
TC075_Validate Tap Notification Row in Notification Inbox_Android
| 1 | Click the Notification Bell in Upper Right Corner in Overview Page | User should be redirected to Notifications Inbox.
| 2 | Select Notification > Tap the notification row | Notification should turn into grey indicating it is read.
| 3 | Click Back | Customer should be redirected to Overview Page.
TC076_Validate Tap Notification Row in Notification Inbox_iOS
| 1 | Click the Notification Bell in Upper Right Corner in Overview Page | User should be redirected to Notifications Inbox.
| 2 | Select Notification > Tap the notification row | Notification should turn into grey indicating it is read.
| 3 | Click Back | Customer should be redirected to Overview Page.
TC077_Payment Transaction
| 1 | Go to Bills and Payments > Pay Bills | Bills and Payments page should be displayed
| 2 | Click on Bill to pay | View Bills page should be displayed
| 3 | Click Pay Now -> Enter payment amount -> Next | Amount to be paid should inputted. Payment Summary should be displayed
| 4 | Click Proceed button | User should be redirected to Payment gateway
| 5 | Select Cards and Enter valid card details | Card details should be inputted
| 6 | Click Pay | Payment Gateway confirmation page should be displayed
| 7 | Click Back to Merchant | User should be redirected to Thank You! Page
TC078_Payment Confirmation Validation
| 1 | Validate Payment Confirmation | Please see reference in Reference Tab: Reference No.: 003
TC079_Validate Acknowledged Email Notification; Modification_Opted
| 1 | Validate Email Notification | Refer to Updated MO Notification Template File: Service App - Sales Email Reference No.: Acknowledgement of SA Receipt, Individual (CA-01-INDe)
TC080_Validate appsflyer tracking after SDK upgrade
| 1 | Validate appsflyer tracking | Appsflyer should be validated after SDK Upgrade.
TC081_Creation of Outage Report_Mobile App
| 1 | Go to Outages & Incidents > Report Streetlight and Safety Concerns | Report an Outage or Incident page should be displayed
| 2 | Select concern type based on scenario | Concern type based on scenario should be selected
| 3 | Upload photo > Click Next | Outage or Incident Location should be displayed
| 4 | Populate required fields > click Next | Contact Information should be displayed
| 5 | Populate required fields > click Submit | Outage report should be created. Reference number should be generated.
TC082_Subscribe to Paperless Billing_Meralco Online
| 1 | Go to Accounts > Manage Accounts | Accounts Page should be displayed
| 2 | Select Customer Account Number (CAN) > Click Subscribe to Paperless Billing button | Customer Account Number (CAN) should be selected. Paperless Billing page should be displayed
| 3 | Click here hyperlink > tick T&C agreement > Next | Account should be enrolled to Paperless Billing; Case number should be generated
TC083_Unsubscribe from Paperless Billing _Meralco Online
| 1 | Go to Accounts > Manage Accounts | Accounts Page should be displayed
| 2 | Select Customer Account Number (CAN) > Click Unsubscribe from Paperless Billing button | Customer Account Number (CAN) should be selected. Cancel Paperless Billing page should be displayed
| 3 | Select Reason why you want to unsubscribe > Click Submit | Account should be unenrolled to Paperless Billing; Case number should be generated
TC084_Subscribe to Paperless Billing_Mobile App
| 1 | Login to Meralco Mobile App> Go to Accounts page | Accounts page should be displayed
| 2 | In Paperless Billing section, Click Subscribe Now | Paperless Billing page should be displayed
| 3 | Tick T&C agreement > Click Submit | Reference Number for subscribing to Paperless Billing should be generated.
| 4 | Go to Activity Tracker > Validate if Reference Number is visible | Reference number should be visible and validated.
TC085_Unsubscribe from Paperless Billing_Mobile App
| 1 | Login to Meralco Online > Go to Accounts page | Accounts page should be displayed
| 2 | In Paperless Billing section, click Unsubscribe | Cancel Paperless Billing page should be displayed
| 3 | Select Reason why you want to unsubscribe > Click Submit | Reference Number for unsubscribing from Paperless Billing should be generated.
| 4 | Go to Activity Tracker > Validate if Reference Number is visible | Reference number should be visible and validated.
TC086_Regular Registration; Mobile App
| 1 | Go to Registration page | User should be directed to Registration Page.
| 2 | Populate all required fields | All required field should be populated.
| 3 | Tick the Terms and Conditions | Terms and Conditions should be ticked.
| 4 | Click Register | User should be redirected to verify page.
| 5 | Verify email Confirmation > Set password | User should be directed to Meralco Online Set Password Page. Password should be saved.
TC087_Validate Redirection to FAQs Outage
| 1 | Go to Dashboard > Outages / Incidents > View / Report Outages > Click FAQ | User redirected to Outage Map; User should be redirected to FAQ Landing Page.
TC088_Validate Inactivity Prompt
| 1 | Validate Inactivity Prompt After 30 Seconds | See reference tab: Reference No.: 008
TC089_Validate Popup Window for PECCBM in Start Service; Yes_Registered
| 1 | Login to Meralco Online | User should be logged in to Meralco Online
| 2 | Click on Request for a Service tile | A popup window should be displayed
| 3 | Validate Popup Message | Please See Reference Tab; Reference No.: 004
| 4 | Click Yes | User should be redirected to PECCBM Customer Landing Page.
TC090_Validate Popup Window for PECCBM in Start Service; No_Registered
| 1 | Login to Meralco Online | User should be logged in to Meralco Online
| 2 | Click on Request for a Service tile | A popup window should be displayed
| 3 | Validate Popup Message | Please See Reference Tab; Reference No.: 004
| 4 | Click No | User should be redirected to Start A Service Page.
TC091_Validate FAQs Updates in Service Phases: 1-Phase and 3-Phase Page
| 1 | Validate FAQ Page | See FAQs Template File for reference; Reference: Requirement No.: 1
TC092_Validate FAQs Updates in Sub-Meter Requests Page
| 1 | Validate FAQ Page | See FAQs Template File for reference; Reference: Requirement No.: 1
TC093_Validate FAQs Updates in New Connection for Residential Page
| 1 | Validate FAQ Page | See FAQs Template File for reference; Reference: Requirement No.: 1
| 2 | Validate FAQ Page_2 | See FAQs Template File for reference; Reference: Requirement No.: 4
| 3 | Validate FAQ Page_3 | See FAQs Template File for reference; Reference: Requirement No.: 8
TC094_Validate FAQs Updates in Voltage Requirements for Residential Services Page
| 1 | Validate FAQ Page | See FAQs Template File for reference; Reference: Requirement No.: 1
TC095_Validate FAQs Updates in Electrical Experts Certified by Meralco (CBM) Page
| 1 | Validate FAQ Page | See FAQs Template File for reference; Reference: Requirement No.: 1
| 2 | Validate FAQ Page_2 | See FAQs Template File for reference; Reference: Requirement No.: 4
| 3 | Validate FAQ Page_3 | See FAQs Template File for reference; Reference: Requirement No.: 6
TC096_Validate FAQs Updates in AMC Services & Other Contractors Page
| 1 | Validate FAQ Page | See FAQs Template File for reference; Reference: Requirement No.: 3
| 2 | Validate FAQ Page_2 | See FAQs Template File for reference; Reference: Requirement No.: 5
| 3 | Validate FAQ Page_3 | See FAQs Template File for reference; Reference: Requirement No.: 7
TC097_Create New Service Application in MO
| 1 | In MO Overview Page, Click Request for a Service Tile > Click No | User should be redirected to Start A Service Page - Contact Information Tab.
| 2 | Populate Required Fields > Click Next | Fields should be populated; New Address Tab should be displayed.
| 3 | Populate Required Fields > Click Next | Fields should be populated; Value Added Services Tab should be displayed.
| 4 | Populate Fields > Click Next | Fields should be populated; Terms and Conditions Tab should be displayed.
| 5 | Tick on I have read and agree to the Meralco Online Terms & Conditions and consent to the processing of my personal data in accordance with the Privacy Policy > Click on captcha | Checkbox should be ticked; Captcha should be validated. *Submit button should be enabled if both are ticked.
| 6 | Click Submit | Confirmation tab should be displayed. Case # should be generated.
TC098_Modification of Electric Service in MO
| 1 | In MO, Go to Accounts > Manage Accounts > Select Service | Service should be selected.
| 2 | Click Change Service Details > Tick Downgrade the kWh > Click Next | Fields should be populated; Value Added Services Tab should be displayed.
| 3 | Populate Required Fields > Click Next | Fields should be populated; Terms and Conditions Tab should be displayed.
| 4 | Tick on I have read and agree to the Meralco Online Terms & Conditions and consent to the processing of my personal data in accordance with the Privacy Policy > Click on captcha | Checkbox should be ticked; Captcha should be validated. *Submit button should be enabled if both are ticked.
| 5 | Click Submit | Confirmation tab should be displayed. Case # should be generated.
TC099_Termination of Electric Service in MO
| 1 | In MO, Go to Accounts > Manage Accounts > Select Service | Service should be selected.
| 2 | Click Stop Electric Service | User should be redirected to Stop Service Page - Request Details Tab.
| 3 | > Click on captcha | Captcha should be validated. *Next button should be enabled if captcha is validated.
| 4 | Click Next | Confirmation tab should be displayed. Case # should be generated.
TC100_Recontract of Electric Service in MO
| 1 | In MO, Go to Accounts > Manage Accounts > Select Service | Service should be selected.
| 2 | Click Reactivate Electric Service | User should be redirected to Reactivate A Service Page - Contact Information Tab.
| 3 | Populate Required Fields > Click Next | Fields should be populated; New Address Tab should be displayed.
| 4 | Populate Required Fields > Click Next | Fields should be populated; Value Added Services Tab should be displayed.
| 5 | Populate Fields > Click Next | Fields should be populated; Terms and Conditions Tab should be displayed.
| 6 | Tick on I have read and agree to the Meralco Online Terms & Conditions and consent to the processing of my personal data in accordance with the Privacy Policy > Click on captcha | Checkbox should be ticked; Captcha should be validated. *Submit button should be enabled if both are ticked.
| 7 | Click Submit | Confirmation tab should be displayed. Case # should be generated.